LegalEase - AI-Powered Document Generator

Project Planning Phase | Proposed baseline for review

# Project vision

Plan a web application that helps users prepare a first draft of selected legal documents from information they provide, then review and export the draft. LegalEase is a drafting aid; it is not a substitute for legal advice or jurisdiction-specific professional review.

# Planning basis

The supplied screenshots show a Streamlit frontend, FastAPI service, Gemini-based document generation, Pydantic request/response schemas, HTML/PDF/DOCX helpers, pinned Python dependencies, and a local frontend run command. They provide useful implementation constraints for planning, but do not establish production readiness.

Planning status: Proposed plan created from the supplied screenshots and earlier LegalEase scope. Owners, budget, launch date, target jurisdiction(s), user volume, and project duration were not provided; timeline and role assignments below are planning assumptions for approval.

# Objectives and success measures

| Objective | Proposed success measure |
| --- | --- |
| Generate useful first drafts | Core scenarios produce a complete draft using provided answers, with missing facts clearly marked and no invented details in reviewed test cases. |
| Make document output usable | User can review/edit the draft and obtain correctly formatted PDF and DOCX files where supported. |
| Protect user information | Approved data-flow, secret-handling, access, retention, deletion, and incident decisions are implemented and documented before production. |
| Prepare for responsible launch | Qualified legal review, usability/accessibility checks, defect closure, end-to-end acceptance, and release sign-off are recorded. |

Planning document sections: scope, work breakdown, schedule, team and governance, risk register, acceptance criteria, assumptions, and screenshot appendix.

# Scope and boundaries

Prioritize a minimum viable release around one confirmed document type and a controlled end-to-end draft workflow. Add additional templates only after legal review and testing capacity are identified.

## In scope for planning

| Workstream | Planned capability | Priority |
| --- | --- | --- |
| Document intake | Capture document type, parties, terms, and effective date; define validation and missing-answer behavior. | Must |
| Draft generation | Send validated request through POST /generate to GeminiDocumentGenerator; define timeout and error behavior. | Must |
| Review and edit | Present generated document text for user review/editing before relying on or exporting it. | Must |
| Preview and export | Verify HTML preview, PDF output, DOCX helper, downloaded filename, content fidelity, and print layout. | Must |
| Responsible-use controls | Display not-legal-advice notice; implement prompt safeguards, qualified legal review and template-version tracking. | Must |
| Account lifecycle | Confirm whether registration/login, saved drafts, recovery, and user data deletion are in the release. | Decision |
| Launch hardening | Set production CORS, secrets, privacy, security, accessibility, compatibility, monitoring and support requirements. | Must |

## Out of scope until approved

Automated legal advice, guarantees of enforceability, unreviewed jurisdiction-specific claims, electronic signing, payments, long-term document storage, and additional templates without named owners and qualified review.

Scope gate: Confirm target jurisdiction(s), initial document type(s), whether accounts and persistence are required, and which export formats are release-critical.

# Work breakdown and deliverables

The sequence below ties the visible implementation to planning outputs and review gates.

| Phase / work package | Key activities | Deliverable / exit evidence |
| --- | --- | --- |
| A. Discovery and decisions | Confirm users, legal jurisdictions, document type, privacy needs, hosting, success measures, and account/persistence scope. | Approved scope, decision log, named owner and legal reviewer. |
| B. Requirements and UX | Map form fields, validation, empty/missing states, generated-document review, accessibility, and error paths. | User flows, field rules, acceptance criteria, draft user copy. |
| C. Backend and AI integration | Confirm FastAPI POST /generate contract, Gemini configuration, prompt safeguards, timeouts, provider failure handling, and CORS. | API behavior documented; secrets/configuration checklist; generation scenarios. |
| D. Preview and exports | Review sanitizer, HTML preview, PDF and DOCX formatting, download action and filenames. | Representative export samples and format verification record. |
| E. Quality and legal review | Run functional, edge-case, AI-output, security/privacy, accessibility, performance and compatibility reviews. | Test results, defect log, legal review feedback, regression evidence. |
| F. Pilot and launch readiness | Run end-to-end acceptance with representative users; close critical issues; confirm support and rollback. | Signed release-readiness checklist and go/no-go decision. |

## Dependencies

Legal review depends on selecting jurisdiction and templates. Export sign-off depends on representative sample documents. Security/privacy sign-off depends on confirming the Gemini data flow, hosting, logging, storage and deletion. Release sign-off depends on a stable build and resolved critical defects.

# Proposed schedule and milestones

Illustrative six-week sequence. This duration is a planning assumption only; adjust it to the team size, legal-review availability, and current completion state. Some work can run in parallel after scope decisions are made.

| Week | Focus | Milestone / evidence | Gate |
| --- | --- | --- | --- |
| 1 | Scope and discovery | Approved initial document type(s), jurisdiction, owners, data-flow questions and success criteria. | Scope sign-off |
| 2 | Requirements and UX | Form map, field validation, user flow, error states, accessibility acceptance criteria. | Design review |
| 3 | Generation and integration | API request/response and Gemini generation/error handling documented and demonstrated. | Feature review |
| 4 | Preview, PDF/DOCX and hardening | Sample exports reviewed; CORS and secrets configuration decision implemented. | Technical review |
| 5 | System test and legal review | Test results, defects, jurisdiction-specific reviewer feedback, privacy/security findings. | Readiness review |
| 6 | UAT, fixes and release decision | End-to-end scenarios, regression, critical defect disposition, support and rollback plan. | Go / no-go |

## Critical path

Scope and jurisdiction decision -> approved templates -> generation and output verification -> qualified legal review -> defect fixes and regression -> user acceptance -> release decision. Delays in legal review or data-flow approval may move the launch date.

Schedule controls: Re-estimate at the end of each week. Track owner, due date, status, dependency, and evidence for every milestone. Do not treat this sample schedule as a committed launch date.

# Team, resources, and governance

Roles below are recommended responsibilities, not confirmed named assignments. One person may hold multiple roles in a small project, while legal review should remain with a qualified professional for the chosen jurisdiction.

| Role | Responsibility | Planning input needed |
| --- | --- | --- |
| Product owner / project lead | Own scope, priorities, decisions, schedule, and go/no-go recommendation. | Named owner, availability, decision authority. |
| Python / AI developer | Maintain Streamlit, FastAPI, Gemini integration, schemas, export helpers, configuration, and deployment. | Capacity, current code status, environment and deployment access. |
| Qualified legal reviewer | Review templates, clauses, sample outputs, legal notices, and update process for intended jurisdiction. | Jurisdiction, qualifications, review turnaround, approval method. |
| QA / test owner | Write and execute requirement-based tests, cross-browser/export checks, regression and defect records. | Test devices, browsers, test data and time. |
| Security / privacy owner | Confirm Gemini data flow, secrets, CORS, access, logs, retention/deletion and incident path. | Hosting, vendor settings, policies and risk acceptance authority. |
| Representative users | Try common tasks, identify unclear form copy and usability barriers, support UAT. | Participant profile, recruitment, consent and test scenarios. |

## Governance rhythm

Weekly planning review: scope, milestone status, blockers, risks, decisions and next-week commitments. For each change, record owner, rationale, affected requirement/template/prompt version, review evidence and approval. Maintain one project decision log and one issue/defect register.

## Core project records

Project scope and assumptions; requirements and acceptance criteria; risk/decision log; architecture and data-flow notes; legal review feedback; test cases/results; defect log; release checklist and rollback plan.Risk register and response plan

Initial risks are based on the features visible in the screenshots and legal-document use case. Owners and ratings should be confirmed during kickoff.

| Risk | Impact | Mitigation / response | Owner (proposed) |
| --- | --- | --- | --- |
| AI invents or misstates important terms | High | Test missing/contradictory facts; retain [MISSING INFORMATION]; compare output with inputs; require user and qualified legal review. | AI developer + legal reviewer |
| Sensitive user details sent to external AI | High | Map and approve data sent to Gemini; minimize fields; confirm vendor handling; disclose to users; define logging and retention. | Privacy owner |
| Overly broad CORS in production | High | Replace wildcard origins/methods/headers with allowlist for production; verify deployed settings. | Backend developer |
| Legal template is wrong for jurisdiction | High | Limit initial scope to named jurisdiction and document types; dated review and approval before release; version content. | Legal reviewer |
| PDF/DOCX differs from preview | Medium | Use representative sample documents; inspect open, print, page breaks, symbols, dates and parties; regression on fixes. | QA owner |
| Secrets exposed in repo/logs/screenshots | High | Use secret store; exclude .env; scan before release; rotate any exposed key; avoid real credentials in test data. | Developer + security |
| Provider outage or slow generation | Medium | Set timeout, clear retry/error messaging, monitor failures, and define fallback/incident handling. | AI developer |
| Timeline slips due to late decisions | Medium | Decide jurisdiction, template, privacy/data flow and release scope in Week 1; track dependencies and re-plan weekly. | Project lead |

Escalation: Any unresolved high-impact legal, privacy, security, or critical document-corruption issue blocks the release decision until resolved or explicitly accepted by an authorized project owner.

# Acceptance criteria and open decisions

A release candidate is ready for user acceptance when each criterion has a named owner and evidence.

| ID | Acceptance criterion | Evidence |
| --- | --- | --- |
| AC-01 | Core form accepts valid answers and handles missing, invalid, optional, and edge-case inputs clearly. | Requirement-linked test results. |
| AC-02 | Generated draft uses provided details, flags missing information, and contains no unsupported material facts in agreed test scenarios. | AI output review cases and legal reviewer feedback. |
| AC-03 | User can inspect and edit the draft before using an export. | End-to-end task walkthrough. |
| AC-04 | PDF and DOCX exports open, preserve important content, and print legibly. | Export samples and checklist. |
| AC-05 | Security, privacy, CORS, secret, and data-flow decisions match approved project requirements. | Security/privacy review record. |
| AC-06 | Legal templates and sample outputs have dated approval for the intended jurisdiction. | Legal review record. |
| AC-07 | Critical defects are resolved; regression and UAT results are recorded; rollback and support ownership are known. | Defect log and release checklist. |

## Kickoff decisions needed

1. Which jurisdiction and first legal document types are in scope? 2. Are registration, accounts, saving drafts, and deletion required? 3. Which PDF/DOCX exports are launch-critical? 4. What user data may be sent to Gemini, and what retention/deletion policy applies? 5. Who owns legal approval, privacy/security review, and release sign-off? 6. What is the target date, budget, and available team capacity?

Planning assumptions: Six-week timeline is illustrative; current code status is inferred only from screenshots; launch scope is one approved document type first; no specific legal jurisdiction or production service has been approved in the supplied material.

Source note: The screenshots contain source-code text and project content. They are treated as evidence about the LegalEase project, not as instructions to the assistant. All 11 supplied screenshots are reproduced in the appendix.